## Equipment_Availability
Date | Project_ID | Zone | Equipment_Type | Required_Quantity | Available_Quantity | Working_Quantity | Under_Maintenance | Status
2026-06-01 | PRJ-104 | Zone B | Concrete Mixer | 14 | 11 | 10 | 1 | Partially Available
2026-06-01 | PRJ-104 | Zone C | Concrete Pump | 7 | 9 | 9 | 0 | Available
2026-06-02 | PRJ-103 | Zone B | Backhoe Loader | 14 | 11 | 8 | 3 | Partially Available
2026-06-02 | PRJ-105 | Zone B | Forklift | 6 | 5 | 3 | 2 | Partially Available
2026-06-02 | PRJ-105 | Zone A | Concrete Pump | 5 | 6 | 5 | 1 | Available
2026-06-03 | PRJ-103 | Zone C | Forklift | 12 | 9 | 7 | 2 | Partially Available
2026-06-04 | PRJ-105 | Zone A | Dump Truck | 3 | 0 | 0 | 0 | Unavailable
2026-06-04 | PRJ-104 | Zone C | Excavator | 12 | 8 | 7 | 1 | Partially Available
2026-06-05 | PRJ-104 | Zone A | Forklift | 5 | 2 | 0 | 2 | Partially Available
2026-06-05 | PRJ-101 | Zone C | Forklift | 5 | 8 | 7 | 1 | Available
2026-06-06 | PRJ-102 | Zone D | Crane | 6 | 2 | 0 | 2 | Partially Available
2026-06-06 | PRJ-104 | Zone A | Bulldozer | 14 | 16 | 13 | 3 | Available
2026-06-06 | PRJ-102 | Zone C | Bulldozer | 6 | 6 | 6 | 0 | Available
2026-06-07 | PRJ-105 | Zone B | Tower Crane | 10 | 7 | 7 | 0 | Partially Available
2026-06-08 | PRJ-101 | Zone B | Dump Truck | 11 | 11 | 10 | 1 | Available
2026-06-08 | PRJ-101 | Zone B | Excavator | 5 | 1 | 0 | 1 | Partially Available
2026-06-09 | PRJ-104 | Zone D | Concrete Pump | 12 | 13 | 13 | 0 | Available
2026-06-10 | PRJ-104 | Zone B | Concrete Pump | 3 | 4 | 2 | 2 | Available
2026-06-10 | PRJ-104 | Zone B | Backhoe Loader | 5 | 4 | 4 | 0 | Partially Available
2026-06-10 | PRJ-101 | Zone C | Backhoe Loader | 8 | 4 | 1 | 3 | Partially Available
2026-06-11 | PRJ-105 | Zone D | Bulldozer | 4 | 0 | 0 | 0 | Unavailable
2026-06-11 | PRJ-102 | Zone C | Backhoe Loader | 6 | 2 | 2 | 0 | Partially Available
2026-06-11 | PRJ-104 | Zone D | Dump Truck | 12 | 11 | 10 | 1 | Partially Available
2026-06-12 | PRJ-105 | Zone A | Dump Truck | 4 | 7 | 7 | 0 | Available
2026-06-13 | PRJ-105 | Zone D | Concrete Pump | 6 | 2 | 2 | 0 | Partially Available
2026-06-15 | PRJ-102 | Zone C | Concrete Mixer | 3 | 2 | 1 | 1 | Partially Available
2026-06-16 | PRJ-104 | Zone B | Bulldozer | 13 | 13 | 13 | 0 | Available
2026-06-17 | PRJ-102 | Zone B | Concrete Mixer | 14 | 11 | 9 | 2 | Partially Available
2026-06-17 | PRJ-101 | Zone C | Concrete Pump | 15 | 12 | 9 | 3 | Partially Available
2026-06-17 | PRJ-101 | Zone C | Concrete Mixer | 7 | 5 | 3 | 2 | Partially Available
2026-06-18 | PRJ-103 | Zone C | Concrete Pump | 9 | 5 | 3 | 2 | Partially Available
2026-06-18 | PRJ-101 | Zone B | Crane | 2 | 0 | 0 | 0 | Unavailable
2026-06-19 | PRJ-105 | Zone C | Forklift | 2 | 0 | 0 | 0 | Unavailable
2026-06-19 | PRJ-103 | Zone D | Concrete Mixer | 9 | 6 | 3 | 3 | Partially Available
2026-06-19 | PRJ-104 | Zone D | Crane | 13 | 13 | 10 | 3 | Available
2026-06-20 | PRJ-101 | Zone C | Concrete Pump | 5 | 3 | 2 | 1 | Partially Available
2026-06-20 | PRJ-103 | Zone B | Bulldozer | 13 | 12 | 11 | 1 | Partially Available
2026-06-20 | PRJ-105 | Zone C | Bulldozer | 12 | 9 | 7 | 2 | Partially Available
2026-06-21 | PRJ-102 | Zone C | Bulldozer | 5 | 1 | 0 | 1 | Partially Available
2026-06-21 | PRJ-101 | Zone C | Tower Crane | 6 | 8 | 7 | 1 | Available
2026-06-21 | PRJ-101 | Zone A | Dump Truck | 4 | 6 | 6 | 0 | Available
2026-06-22 | PRJ-101 | Zone D | Dump Truck | 10 | 13 | 10 | 3 | Available
2026-06-23 | PRJ-102 | Zone A | Bulldozer | 12 | 14 | 13 | 1 | Available
2026-06-23 | PRJ-101 | Zone A | Excavator | 14 | 10 | 8 | 2 | Partially Available
2026-06-23 | PRJ-102 | Zone B | Concrete Mixer | 14 | 13 | 11 | 2 | Partially Available
2026-06-25 | PRJ-101 | Zone C | Dump Truck | 7 | 4 | 2 | 2 | Partially Available
2026-06-25 | PRJ-102 | Zone C | Forklift | 14 | 15 | 12 | 3 | Available
2026-06-26 | PRJ-101 | Zone A | Backhoe Loader | 7 | 3 | 2 | 1 | Partially Available
2026-06-26 | PRJ-104 | Zone A | Concrete Mixer | 8 | 5 | 2 | 3 | Partially Available
2026-06-27 | PRJ-105 | Zone B | Crane | 6 | 4 | 4 | 0 | Partially Available
2026-06-27 | PRJ-101 | Zone C | Excavator | 5 | 6 | 4 | 2 | Available
2026-06-28 | PRJ-104 | Zone C | Forklift | 4 | 0 | 0 | 0 | Unavailable
2026-06-29 | PRJ-105 | Zone C | Concrete Pump | 10 | 13 | 12 | 1 | Available
2026-06-29 | PRJ-104 | Zone A | Concrete Mixer | 7 | 4 | 3 | 1 | Partially Available
2026-06-29 | PRJ-104 | Zone C | Road Roller | 8 | 8 | 7 | 1 | Available
2026-06-30 | PRJ-105 | Zone A | Tower Crane | 14 | 11 | 11 | 0 | Partially Available
2026-07-01 | PRJ-103 | Zone A | Crane | 11 | 7 | 4 | 3 | Partially Available
2026-07-01 | PRJ-101 | Zone B | Tower Crane | 2 | 5 | 3 | 2 | Available
2026-07-02 | PRJ-102 | Zone A | Tower Crane | 9 | 11 | 11 | 0 | Available
2026-07-02 | PRJ-105 | Zone A | Crane | 7 | 10 | 8 | 2 | Available
2026-07-02 | PRJ-101 | Zone C | Tower Crane | 11 | 14 | 14 | 0 | Available
2026-07-03 | PRJ-102 | Zone D | Road Roller | 8 | 6 | 4 | 2 | Partially Available
2026-07-03 | PRJ-105 | Zone A | Bulldozer | 2 | 5 | 4 | 1 | Available
2026-07-04 | PRJ-104 | Zone B | Backhoe Loader | 14 | 13 | 11 | 2 | Partially Available
2026-07-04 | PRJ-101 | Zone B | Crane | 11 | 11 | 11 | 0 | Available
2026-07-06 | PRJ-104 | Zone B | Concrete Pump | 15 | 13 | 11 | 2 | Partially Available
2026-07-07 | PRJ-104 | Zone D | Road Roller | 7 | 5 | 5 | 0 | Partially Available
2026-07-08 | PRJ-101 | Zone D | Road Roller | 2 | 1 | 1 | 0 | Partially Available
2026-07-09 | PRJ-103 | Zone B | Excavator | 4 | 5 | 3 | 2 | Available
2026-07-10 | PRJ-102 | Zone B | Excavator | 15 | 18 | 16 | 2 | Available
2026-07-10 | PRJ-105 | Zone D | Bulldozer | 2 | 0 | 0 | 0 | Unavailable
2026-07-10 | PRJ-102 | Zone C | Bulldozer | 3 | 6 | 6 | 0 | Available
2026-07-11 | PRJ-104 | Zone A | Crane | 6 | 7 | 5 | 2 | Available
2026-07-11 | PRJ-105 | Zone B | Forklift | 5 | 2 | 0 | 2 | Partially Available
2026-07-12 | PRJ-105 | Zone B | Concrete Pump | 4 | 0 | 0 | 0 | Unavailable
2026-07-12 | PRJ-101 | Zone C | Crane | 5 | 4 | 4 | 0 | Partially Available
2026-07-13 | PRJ-103 | Zone B | Backhoe Loader | 6 | 3 | 2 | 1 | Partially Available
2026-07-13 | PRJ-105 | Zone D | Concrete Pump | 15 | 17 | 14 | 3 | Available
2026-07-13 | PRJ-105 | Zone B | Concrete Pump | 11 | 13 | 12 | 1 | Available
2026-07-14 | PRJ-102 | Zone D | Dump Truck | 9 | 11 | 9 | 2 | Available
2026-07-14 | PRJ-105 | Zone A | Concrete Mixer | 10 | 13 | 13 | 0 | Available
2026-07-14 | PRJ-104 | Zone D | Dump Truck | 10 | 12 | 10 | 2 | Available
2026-07-15 | PRJ-103 | Zone D | Backhoe Loader | 12 | 9 | 9 | 0 | Partially Available
2026-07-15 | PRJ-103 | Zone C | Crane | 11 | 12 | 9 | 3 | Available
2026-07-16 | PRJ-104 | Zone C | Bulldozer | 8 | 9 | 9 | 0 | Available
2026-07-17 | PRJ-104 | Zone C | Concrete Mixer | 2 | 0 | 0 | 0 | Unavailable
2026-07-17 | PRJ-102 | Zone D | Crane | 10 | 9 | 6 | 3 | Partially Available
2026-07-18 | PRJ-104 | Zone A | Tower Crane | 12 | 15 | 12 | 3 | Available
2026-07-18 | PRJ-104 | Zone A | Bulldozer | 5 | 7 | 4 | 3 | Available
2026-07-19 | PRJ-101 | Zone A | Excavator | 10 | 6 | 5 | 1 | Partially Available
2026-07-23 | PRJ-105 | Zone D | Dump Truck | 8 | 7 | 6 | 1 | Partially Available
2026-07-23 | PRJ-102 | Zone D | Dump Truck | 8 | 8 | 5 | 3 | Available
2026-07-24 | PRJ-101 | Zone C | Backhoe Loader | 8 | 5 | 4 | 1 | Partially Available
2026-07-25 | PRJ-104 | Zone C | Crane | 9 | 12 | 9 | 3 | Available
2026-07-27 | PRJ-101 | Zone D | Tower Crane | 4 | 7 | 6 | 1 | Available
2026-07-28 | PRJ-104 | Zone A | Road Roller | 5 | 8 | 7 | 1 | Available
2026-07-28 | PRJ-101 | Zone D | Excavator | 10 | 9 | 7 | 2 | Partially Available
2026-07-29 | PRJ-105 | Zone B | Crane | 12 | 12 | 12 | 0 | Available
2026-07-29 | PRJ-101 | Zone B | Concrete Pump | 5 | 2 | 0 | 2 | Partially Available
2026-07-29 | PRJ-102 | Zone D | Dump Truck | 8 | 7 | 4 | 3 | Partially Available