## Labour_Availability
Date | Project_ID | Zone | Task | Labour_Type | Required_Labour | Available_Labour | Shift | Status
2026-06-01 | PRJ-105 | Zone A | Brickwork | Plumber | 18 | 19 | Night | Completed
2026-06-02 | PRJ-104 | Zone D | Foundation | Painter | 28 | 29 | Evening | Completed
2026-06-02 | PRJ-103 | Zone D | Painting | Helper | 9 | 12 | Morning | Pending
2026-06-03 | PRJ-101 | Zone C | Painting | Plumber | 13 | 10 | Night | Active
2026-06-03 | PRJ-103 | Zone A | Painting | Electrician | 25 | 20 | Evening | Completed
2026-06-03 | PRJ-104 | Zone C | Electrical Wiring | Plumber | 23 | 16 | Night | Pending
2026-06-05 | PRJ-105 | Zone C | Brickwork | Helper | 25 | 22 | Night | Completed
2026-06-06 | PRJ-101 | Zone B | Plastering | Welder | 27 | 26 | Night | Active
2026-06-06 | PRJ-103 | Zone A | Foundation | Painter | 24 | 22 | Morning | Pending
2026-06-07 | PRJ-103 | Zone D | Roofing | Plumber | 22 | 14 | Morning | Pending
2026-06-07 | PRJ-105 | Zone A | Brickwork | Plumber | 5 | 7 | Morning | Completed
2026-06-07 | PRJ-101 | Zone D | Painting | Plumber | 16 | 21 | Evening | Completed
2026-06-08 | PRJ-104 | Zone B | Excavation | Bar Bender | 21 | 25 | Evening | Completed
2026-06-08 | PRJ-102 | Zone D | Foundation | Helper | 13 | 11 | Night | Active
2026-06-09 | PRJ-102 | Zone C | Electrical Wiring | Carpenter | 15 | 8 | Evening | Pending
2026-06-09 | PRJ-103 | Zone D | Painting | Electrician | 17 | 11 | Evening | Pending
2026-06-09 | PRJ-105 | Zone C | Flooring | Bar Bender | 29 | 28 | Night | Completed
2026-06-09 | PRJ-101 | Zone A | Brickwork | Carpenter | 20 | 19 | Night | Active
2026-06-12 | PRJ-104 | Zone C | Painting | Welder | 5 | 1 | Evening | Completed
2026-06-12 | PRJ-105 | Zone D | Foundation | Plumber | 29 | 32 | Morning | Completed
2026-06-13 | PRJ-104 | Zone A | Excavation | Plumber | 12 | 4 | Evening | Completed
2026-06-14 | PRJ-105 | Zone C | Flooring | Welder | 17 | 21 | Evening | Pending
2026-06-14 | PRJ-101 | Zone A | Roofing | Electrician | 28 | 25 | Evening | Completed
2026-06-14 | PRJ-102 | Zone A | Electrical Wiring | Painter | 20 | 19 | Morning | Active
2026-06-15 | PRJ-101 | Zone B | Excavation | Bar Bender | 20 | 21 | Morning | Completed
2026-06-15 | PRJ-102 | Zone B | Brickwork | Bar Bender | 16 | 19 | Evening | Completed
2026-06-15 | PRJ-101 | Zone B | Concreting | Plumber | 6 | 3 | Morning | Active
2026-06-16 | PRJ-104 | Zone B | Excavation | Carpenter | 12 | 14 | Night | Pending
2026-06-17 | PRJ-104 | Zone D | Excavation | Mason | 9 | 12 | Morning | Active
2026-06-17 | PRJ-104 | Zone C | Roofing | Welder | 29 | 33 | Morning | Active
2026-06-17 | PRJ-105 | Zone D | Painting | Plumber | 20 | 25 | Night | Completed
2026-06-18 | PRJ-103 | Zone C | Excavation | Bar Bender | 6 | 10 | Night | Pending
2026-06-18 | PRJ-101 | Zone B | Excavation | Plumber | 26 | 28 | Morning | Completed
2026-06-18 | PRJ-102 | Zone A | Electrical Wiring | Welder | 14 | 19 | Morning | Completed
2026-06-18 | PRJ-105 | Zone C | Brickwork | Plumber | 27 | 28 | Evening | Active
2026-06-19 | PRJ-103 | Zone C | Excavation | Electrician | 11 | 7 | Morning | Active
2026-06-19 | PRJ-104 | Zone A | Foundation | Helper | 26 | 20 | Evening | Completed
2026-06-19 | PRJ-105 | Zone A | Plumbing Work | Mason | 10 | 2 | Morning | Pending
2026-06-20 | PRJ-102 | Zone B | Foundation | Plumber | 30 | 34 | Evening | Completed
2026-06-20 | PRJ-103 | Zone A | Concreting | Electrician | 22 | 20 | Morning | Pending
2026-06-21 | PRJ-104 | Zone B | Electrical Wiring | Welder | 11 | 7 | Evening | Active
2026-06-22 | PRJ-103 | Zone B | Concreting | Helper | 4 | 0 | Morning | Active
2026-06-23 | PRJ-103 | Zone A | Excavation | Painter | 21 | 19 | Morning | Completed
2026-06-23 | PRJ-104 | Zone B | Painting | Carpenter | 28 | 28 | Morning | Completed
2026-06-24 | PRJ-101 | Zone B | Electrical Wiring | Mason | 9 | 5 | Morning | Pending
2026-06-25 | PRJ-102 | Zone B | Foundation | Electrician | 19 | 17 | Evening | Active
2026-06-25 | PRJ-105 | Zone B | Plumbing Work | Mason | 12 | 14 | Morning | Active
2026-06-26 | PRJ-103 | Zone D | Excavation | Welder | 25 | 27 | Morning | Active
2026-06-28 | PRJ-104 | Zone D | Foundation | Electrician | 15 | 13 | Morning | Completed
2026-06-29 | PRJ-101 | Zone C | Flooring | Electrician | 14 | 8 | Morning | Completed
2026-06-30 | PRJ-103 | Zone B | Plumbing Work | Painter | 24 | 29 | Morning | Pending
2026-07-01 | PRJ-105 | Zone B | Foundation | Electrician | 20 | 25 | Morning | Active
2026-07-02 | PRJ-101 | Zone B | Plastering | Helper | 6 | 7 | Morning | Active
2026-07-02 | PRJ-103 | Zone C | Electrical Wiring | Helper | 10 | 7 | Night | Active
2026-07-02 | PRJ-103 | Zone D | Plastering | Welder | 4 | 2 | Morning | Pending
2026-07-02 | PRJ-104 | Zone B | Electrical Wiring | Carpenter | 16 | 18 | Morning | Pending
2026-07-02 | PRJ-104 | Zone A | Plastering | Bar Bender | 19 | 14 | Morning | Completed
2026-07-03 | PRJ-103 | Zone B | Plastering | Painter | 7 | 12 | Morning | Pending
2026-07-04 | PRJ-102 | Zone D | Flooring | Plumber | 10 | 3 | Night | Completed
2026-07-04 | PRJ-101 | Zone A | Excavation | Helper | 12 | 12 | Night | Completed
2026-07-05 | PRJ-102 | Zone A | Foundation | Mason | 5 | 2 | Morning | Active
2026-07-05 | PRJ-105 | Zone A | Brickwork | Bar Bender | 4 | 2 | Morning | Completed
2026-07-05 | PRJ-101 | Zone B | Roofing | Bar Bender | 18 | 16 | Night | Pending
2026-07-06 | PRJ-104 | Zone C | Electrical Wiring | Helper | 14 | 11 | Morning | Active
2026-07-06 | PRJ-105 | Zone C | Concreting | Plumber | 13 | 18 | Night | Active
2026-07-06 | PRJ-105 | Zone D | Concreting | Bar Bender | 21 | 17 | Evening | Active
2026-07-07 | PRJ-104 | Zone C | Foundation | Welder | 23 | 25 | Evening | Active
2026-07-07 | PRJ-104 | Zone D | Painting | Electrician | 19 | 14 | Morning | Pending
2026-07-07 | PRJ-103 | Zone C | Plastering | Electrician | 10 | 9 | Morning | Completed
2026-07-08 | PRJ-101 | Zone B | Roofing | Painter | 12 | 16 | Evening | Active
2026-07-09 | PRJ-101 | Zone D | Excavation | Electrician | 12 | 16 | Evening | Active
2026-07-09 | PRJ-103 | Zone D | Concreting | Electrician | 17 | 14 | Evening | Pending
2026-07-09 | PRJ-103 | Zone B | Electrical Wiring | Welder | 10 | 13 | Evening | Active
2026-07-09 | PRJ-102 | Zone D | Brickwork | Plumber | 6 | 8 | Night | Pending
2026-07-10 | PRJ-104 | Zone D | Concreting | Plumber | 28 | 21 | Night | Pending
2026-07-11 | PRJ-103 | Zone B | Painting | Carpenter | 7 | 0 | Night | Active
2026-07-12 | PRJ-104 | Zone A | Brickwork | Helper | 26 | 25 | Morning | Completed
2026-07-13 | PRJ-102 | Zone C | Roofing | Mason | 16 | 18 | Evening | Completed
2026-07-13 | PRJ-104 | Zone C | Excavation | Carpenter | 17 | 14 | Morning | Completed
2026-07-14 | PRJ-101 | Zone D | Foundation | Mason | 27 | 27 | Morning | Active
2026-07-14 | PRJ-102 | Zone B | Foundation | Mason | 13 | 8 | Morning | Completed
2026-07-15 | PRJ-102 | Zone A | Electrical Wiring | Electrician | 30 | 32 | Night | Active
2026-07-15 | PRJ-105 | Zone C | Flooring | Painter | 11 | 7 | Evening | Pending
2026-07-16 | PRJ-105 | Zone A | Excavation | Helper | 13 | 14 | Night | Active
2026-07-16 | PRJ-102 | Zone A | Foundation | Painter | 24 | 16 | Morning | Pending
2026-07-17 | PRJ-101 | Zone B | Painting | Plumber | 14 | 18 | Night | Completed
2026-07-17 | PRJ-101 | Zone B | Painting | Plumber | 10 | 7 | Night | Completed
2026-07-17 | PRJ-103 | Zone D | Flooring | Bar Bender | 20 | 22 | Night | Pending
2026-07-19 | PRJ-104 | Zone C | Brickwork | Welder | 16 | 12 | Morning | Pending
2026-07-20 | PRJ-105 | Zone C | Flooring | Mason | 20 | 12 | Morning | Completed
2026-07-20 | PRJ-104 | Zone B | Electrical Wiring | Welder | 28 | 28 | Morning | Pending
2026-07-21 | PRJ-105 | Zone A | Roofing | Bar Bender | 25 | 23 | Night | Completed
2026-07-22 | PRJ-103 | Zone A | Painting | Painter | 14 | 12 | Morning | Pending
2026-07-23 | PRJ-104 | Zone C | Flooring | Carpenter | 19 | 12 | Evening | Active
2026-07-24 | PRJ-102 | Zone B | Plastering | Welder | 4 | 5 | Night | Active
2026-07-25 | PRJ-105 | Zone B | Flooring | Plumber | 30 | 28 | Evening | Completed
2026-07-27 | PRJ-105 | Zone A | Plumbing Work | Carpenter | 26 | 20 | Evening | Active
2026-07-27 | PRJ-101 | Zone A | Excavation | Carpenter | 8 | 4 | Evening | Completed
2026-07-27 | PRJ-103 | Zone B | Foundation | Plumber | 30 | 34 | Night | Active
2026-07-28 | PRJ-104 | Zone D | Electrical Wiring | Plumber | 9 | 12 | Night | Completed