## Material_Availability
Date | Project_ID | Zone | Material_Type | Unit | Required_Quantity | Available_Quantity | Status
2026-06-01 | PRJ-103 | Zone D | Bricks | Pieces | 3310 | 2643 | Partially Available
2026-06-02 | PRJ-104 | Zone A | Steel | Tons | 7 | 7 | Available
2026-06-02 | PRJ-103 | Zone D | Bricks | Pieces | 6992 | 8087 | Available
2026-06-05 | PRJ-101 | Zone D | Sand | Cubic Meter | 39 | 48 | Available
2026-06-05 | PRJ-102 | Zone C | RMC (Ready Mix Concrete) | Cubic Meter | 57 | 47 | Partially Available
2026-06-05 | PRJ-101 | Zone A | Bitumen | Tons | 7 | 4 | Partially Available
2026-06-05 | PRJ-105 | Zone D | Timber | Cubic Meter | 20 | 12 | Partially Available
2026-06-06 | PRJ-101 | Zone C | Bitumen | Tons | 4 | 2 | Partially Available
2026-06-07 | PRJ-105 | Zone B | RMC (Ready Mix Concrete) | Cubic Meter | 23 | 24 | Available
2026-06-07 | PRJ-102 | Zone A | Sand | Cubic Meter | 13 | 13 | Available
2026-06-07 | PRJ-101 | Zone C | Aggregate | Cubic Meter | 34 | 31 | Partially Available
2026-06-08 | PRJ-104 | Zone B | Timber | Cubic Meter | 17 | 16 | Partially Available
2026-06-08 | PRJ-105 | Zone D | Sand | Cubic Meter | 40 | 42 | Available
2026-06-09 | PRJ-103 | Zone C | Paint | Cans | 136 | 102 | Partially Available
2026-06-09 | PRJ-101 | Zone C | Cement | Bags | 245 | 264 | Available
2026-06-10 | PRJ-101 | Zone D | Steel | Tons | 5 | 5 | Available
2026-06-10 | PRJ-105 | Zone D | Aggregate | Cubic Meter | 47 | 55 | Available
2026-06-10 | PRJ-105 | Zone C | Tiles | Pieces | 334 | 201 | Partially Available
2026-06-10 | PRJ-105 | Zone D | Paint | Cans | 22 | 17 | Partially Available
2026-06-11 | PRJ-103 | Zone B | Tiles | Pieces | 1043 | 1121 | Available
2026-06-11 | PRJ-104 | Zone A | Sand | Cubic Meter | 83 | 95 | Available
2026-06-11 | PRJ-104 | Zone C | Tiles | Pieces | 2112 | 1861 | Partially Available
2026-06-11 | PRJ-104 | Zone B | Tiles | Pieces | 1912 | 1997 | Available
2026-06-11 | PRJ-102 | Zone B | Timber | Cubic Meter | 12 | 10 | Partially Available
2026-06-12 | PRJ-103 | Zone C | Sand | Cubic Meter | 90 | 75 | Partially Available
2026-06-13 | PRJ-103 | Zone A | Bricks | Pieces | 1563 | 1321 | Partially Available
2026-06-14 | PRJ-104 | Zone C | Bricks | Pieces | 9432 | 9322 | Partially Available
2026-06-14 | PRJ-101 | Zone C | RMC (Ready Mix Concrete) | Cubic Meter | 39 | 39 | Available
2026-06-15 | PRJ-101 | Zone B | Cement | Bags | 74 | 78 | Available
2026-06-15 | PRJ-105 | Zone D | RMC (Ready Mix Concrete) | Cubic Meter | 56 | 65 | Available
2026-06-16 | PRJ-105 | Zone D | Paint | Cans | 137 | 119 | Partially Available
2026-06-17 | PRJ-101 | Zone D | Tiles | Pieces | 767 | 531 | Partially Available
2026-06-17 | PRJ-102 | Zone D | RMC (Ready Mix Concrete) | Cubic Meter | 25 | 28 | Available
2026-06-17 | PRJ-103 | Zone B | Steel | Tons | 2 | 1 | Partially Available
2026-06-18 | PRJ-104 | Zone D | RMC (Ready Mix Concrete) | Cubic Meter | 57 | 50 | Partially Available
2026-06-20 | PRJ-105 | Zone B | Bricks | Pieces | 7834 | 6910 | Partially Available
2026-06-20 | PRJ-101 | Zone B | Cement | Bags | 463 | 300 | Partially Available
2026-06-22 | PRJ-104 | Zone A | Paint | Cans | 100 | 87 | Partially Available
2026-06-22 | PRJ-103 | Zone D | Sand | Cubic Meter | 78 | 69 | Partially Available
2026-06-23 | PRJ-104 | Zone C | Cement | Bags | 132 | 82 | Partially Available
2026-06-25 | PRJ-103 | Zone A | Bricks | Pieces | 8603 | 10803 | Available
2026-06-26 | PRJ-102 | Zone B | Paint | Cans | 66 | 68 | Available
2026-06-27 | PRJ-103 | Zone B | Bricks | Pieces | 3795 | 3325 | Partially Available
2026-06-27 | PRJ-103 | Zone D | Sand | Cubic Meter | 85 | 51 | Partially Available
2026-06-28 | PRJ-103 | Zone A | Tiles | Pieces | 1110 | 1046 | Partially Available
2026-06-30 | PRJ-102 | Zone B | Steel | Tons | 14 | 15 | Available
2026-07-01 | PRJ-104 | Zone A | Timber | Cubic Meter | 18 | 15 | Partially Available
2026-07-01 | PRJ-103 | Zone A | Sand | Cubic Meter | 66 | 76 | Available
2026-07-01 | PRJ-103 | Zone C | Bitumen | Tons | 3 | 2 | Partially Available
2026-07-02 | PRJ-102 | Zone C | RMC (Ready Mix Concrete) | Cubic Meter | 59 | 55 | Partially Available
2026-07-02 | PRJ-105 | Zone B | Steel | Tons | 19 | 19 | Available
2026-07-03 | PRJ-102 | Zone B | Tiles | Pieces | 2931 | 2265 | Partially Available
2026-07-03 | PRJ-104 | Zone C | Tiles | Pieces | 1502 | 1947 | Available
2026-07-03 | PRJ-103 | Zone C | Steel | Tons | 23 | 27 | Available
2026-07-04 | PRJ-105 | Zone B | Aggregate | Cubic Meter | 47 | 51 | Available
2026-07-04 | PRJ-104 | Zone A | Aggregate | Cubic Meter | 58 | 64 | Available
2026-07-05 | PRJ-103 | Zone D | Paint | Cans | 62 | 38 | Partially Available
2026-07-05 | PRJ-101 | Zone D | Bitumen | Tons | 10 | 6 | Partially Available
2026-07-05 | PRJ-102 | Zone D | Aggregate | Cubic Meter | 62 | 45 | Partially Available
2026-07-06 | PRJ-104 | Zone A | Steel | Tons | 16 | 18 | Available
2026-07-07 | PRJ-105 | Zone C | Steel | Tons | 19 | 19 | Available
2026-07-07 | PRJ-105 | Zone D | Paint | Cans | 60 | 56 | Partially Available
2026-07-07 | PRJ-105 | Zone A | RMC (Ready Mix Concrete) | Cubic Meter | 25 | 24 | Partially Available
2026-07-08 | PRJ-105 | Zone D | Bitumen | Tons | 4 | 4 | Available
2026-07-08 | PRJ-101 | Zone B | Cement | Bags | 390 | 436 | Available
2026-07-09 | PRJ-101 | Zone D | Timber | Cubic Meter | 3 | 3 | Available
2026-07-09 | PRJ-103 | Zone D | Timber | Cubic Meter | 7 | 4 | Partially Available
2026-07-11 | PRJ-104 | Zone C | Steel | Tons | 3 | 2 | Partially Available
2026-07-11 | PRJ-101 | Zone D | Paint | Cans | 139 | 143 | Available
2026-07-13 | PRJ-102 | Zone A | Cement | Bags | 290 | 349 | Available
2026-07-13 | PRJ-103 | Zone A | Sand | Cubic Meter | 95 | 82 | Partially Available
2026-07-14 | PRJ-102 | Zone C | Tiles | Pieces | 847 | 527 | Partially Available
2026-07-14 | PRJ-102 | Zone D | Cement | Bags | 63 | 54 | Partially Available
2026-07-15 | PRJ-103 | Zone A | Steel | Tons | 22 | 27 | Available
2026-07-15 | PRJ-105 | Zone B | Paint | Cans | 71 | 91 | Available
2026-07-16 | PRJ-105 | Zone C | RMC (Ready Mix Concrete) | Cubic Meter | 18 | 20 | Available
2026-07-18 | PRJ-103 | Zone D | Tiles | Pieces | 2722 | 2475 | Partially Available
2026-07-18 | PRJ-102 | Zone C | Aggregate | Cubic Meter | 41 | 42 | Available
2026-07-19 | PRJ-102 | Zone D | Tiles | Pieces | 2849 | 3202 | Available
2026-07-19 | PRJ-102 | Zone A | RMC (Ready Mix Concrete) | Cubic Meter | 24 | 18 | Partially Available
2026-07-20 | PRJ-103 | Zone B | Paint | Cans | 58 | 61 | Available
2026-07-20 | PRJ-105 | Zone A | Bricks | Pieces | 4417 | 4733 | Available
2026-07-21 | PRJ-105 | Zone B | Paint | Cans | 141 | 102 | Partially Available
2026-07-21 | PRJ-103 | Zone A | Steel | Tons | 8 | 8 | Available
2026-07-21 | PRJ-105 | Zone D | Cement | Bags | 57 | 49 | Partially Available
2026-07-22 | PRJ-102 | Zone D | Aggregate | Cubic Meter | 27 | 30 | Available
2026-07-22 | PRJ-104 | Zone B | Bricks | Pieces | 7536 | 6554 | Partially Available
2026-07-23 | PRJ-102 | Zone C | Timber | Cubic Meter | 2 | 1 | Partially Available
2026-07-24 | PRJ-103 | Zone A | Aggregate | Cubic Meter | 16 | 19 | Available
2026-07-25 | PRJ-105 | Zone A | Tiles | Pieces | 1025 | 1124 | Available
2026-07-26 | PRJ-103 | Zone D | Aggregate | Cubic Meter | 23 | 19 | Partially Available
2026-07-26 | PRJ-103 | Zone C | Steel | Tons | 22 | 17 | Partially Available
2026-07-27 | PRJ-102 | Zone A | Tiles | Pieces | 795 | 527 | Partially Available
2026-07-27 | PRJ-101 | Zone D | Cement | Bags | 387 | 389 | Available
2026-07-28 | PRJ-105 | Zone D | Bricks | Pieces | 3492 | 2240 | Partially Available
2026-07-28 | PRJ-103 | Zone D | Timber | Cubic Meter | 8 | 6 | Partially Available
2026-07-29 | PRJ-102 | Zone C | Steel | Tons | 9 | 7 | Partially Available
2026-07-29 | PRJ-105 | Zone A | Bitumen | Tons | 3 | 3 | Available
2026-07-30 | PRJ-101 | Zone B | Sand | Cubic Meter | 64 | 55 | Partially Available
2026-07-30 | PRJ-105 | Zone C | Timber | Cubic Meter | 18 | 15 | Partially Available